## Estimates
Epic | Task | Description | Estimate (Days) | Notes
1: Extension Scaffolding & Configuration Strategy | TASK-101: Create Extension Manifest and Scaffolding | Initialize the Chrome extension with `manifest.json` targeting Manifest V3. | 0.5 | manifest.json
| TASK-102: Develop Options Page (UI & Logic) | Create the `options.html` and `options.js` for manual testing and configuration fallback. | 0.5 | options.html, options.js
| TASK-103: Implement Admin Config Loader | Build the priority-based configuration loader. | 0.5 | config-loader.js
| TASK-104: Build Toolbar Popup UI | Create `popup.html` and `popup.js` to show extension status. | 0.5 | popup.html, popup.js
2: Content Script & UI Override Layer | TASK-201: Login Interception & Navigation Blocking | Inject `content-script.js` into `id.atlassian.com/login/authorize` and block default redirection. | 0.5 | content-script.js injection
| TASK-202: Extract Atlassian Account ID | Extract the required user ID for the API step. | 0.5 | __aid_user_id cookie logic
| TASK-203: Develop Interstitial Overlay Framework | Build the full-screen overlay UI and CSS animations to hide the native login page transition. | 1 | DOM injection, CSS animations
3: API & Service Worker Architecture | TASK-301: Setup Service Worker Message Listeners | Establish a message-passing bridge between `content-script.js` and `service-worker.js`. | 0.5 | chrome.runtime.onMessage context
| TASK-302: API Integration: Add to Group (POST) | Execute the HTTP POST call to the Atlassian API from the background worker. | 0.5 | fetch and abort controllers
| TASK-303: API Integration: Verify Membership (GET) | Execute the HTTP GET call to verify if the user was successfully added to the group. | 0.5 | fetch and abort controllers
4: Orchestration, Flow Control & Security | TASK-401: Implement Core Login Intercept Flow (State Machine) | Write the master state machine that ties together the 5 steps in `handleLoginRedirect()`. | 1 | handleLoginRedirect flow
| TASK-402: Verification Polling & Retry Logic | Create the polling mechanism due to API eventual consistency. | 0.5 | Retry loop
| TASK-403: Security: Open Redirect Protection | Ensure the `continueUrl` redirect does not allow phishing attacks. | 0.5 | Domain allowlist and validation
| TASK-404: Global Error Handling & Recovery Escape Hatches | Catch global errors and assure the user is never stuck in the native login redirect loop. | 1 | Global catch and auto-redirect
5: Quality Assurance & Documentation | TASK-501: Code Cleanup & Logging Hygiene | Strip PII and secure tokens out of application console logs. | 0.5 | Remove PII, standardize logging
| TASK-502: User & Admin Documentation writing (README, QUICKSTART) | Create documentation covering setup, testing, and operations (`README.md`, `QUICKSTART.md`). | 0.5 | README.md, QUICKSTART.md
| TASK-503: Technical specification writing (TECHNICAL.md) | Document system architecture, storage schemas, and security lifecycles. | 1 | Technical documentation (Architecture, runtime, etc)
| TASK-504: Test Planning (TEST-PLAN.md) | Draft explicit test cases covering happy paths and failure conditions. | 0.5 | Test plan (Happy path, error state test cases)
| TASK-505: Testing (Manual & Edge Cases Execution) | Execute the regression and testing suite outlined in the Test Plan. | 1.5 | Cross-checking with TEST-PLAN
Total |  |  | 12.5